## Slide 1: Grant Management Workshop 2 After the Money: Planning, Milestones, and Financials
Presented By: Heather Himmelberger
www.southwestefc.unm.edu
www.efcnetwork.org
This program is made possible under a cooperative agreement with the U.S. EPA.
Chart: 
| Category 1 | Category 2 | Category 3 | Category 4
Series 1 | 4.3 | 2.5 | 3.5 | 4.5
Series 2 | 2.4 | 4.4 | 1.8 | 2.8
Series 3 | 2 | 2 | 3 | 5

## Slide 2: Today is Part 2 of a Two-Part Series On Grants and Grant/Loan Management
Before the Money
November 8, 2018
After the Money
January 17, 2018

## Slide 3: Access Part 1 on the EFCN Website (Either Slides or Recording)
https://efcnetwork.org/events/webinar-grant-writing-101/

## Slide 4: Overlap Between Parts 1 and 2
Seeking Funding for Projects
After Funding Has Been Received
Pre-Planning
Planning
Design
These three steps may be either before the money or after

## Slide 5: Overlap Between Parts 1 and 2
Seeking Funding for Projects
After Funding Has Been Received
One More Item to Note: We Called this Grant’s Management, But It Applies Equally To Any Kind of Funding: Grants, Loans, Other

## Slide 6: After the Funding: Topics We’ll Cover
A Little Bit of Finance
Working with Engineers, Alternatives Evaluation

## Slide 7: Let’s Start With Planning

## Slide 8: Why Does Planning Matter So Much?
Pre-planning/ Planning
Design
Construction
Operation of the Facility

## Slide 9: The Greatest Influence at the Least Cost Occurs at the Earliest Stages – Planning & Pre-Planning

## Slide 10: Let’s Look at an Example
The Planner Indicates the Location of a Storage Tank on the Hill Behind Town
The Engineer Designs the Project With That Tank Location
The Construction Contractor Builds the Tank in That Location
The Operator Realizes That the Tank Location Has Two Problems. The Location is Inaccessible in Bad Weather (Rain or Snow) and the Elevation Means That Another Tank Overflows.
$
$$
$$$$
$$$$$$$$$$$
Highest cost
Least Influence

## Slide 11
THE PLANNER INDICATES THE LOCATION OF A STORAGE TANK ON THE HILL BEHIND TOWN
THE ENGINEER DESIGNS THE PROJECT WITH THAT TANK LOCATION
THE CONSTRUCTION CONTRACTOR BUILDS THE TANK IN THAT LOCATION
THE OPERATOR REALIZES THAT THE TANK LOCATION HAS TWO PROBLEMS. THE LOCATION IS INACCESSIBLE IN BAD WEATHER (RAIN OR SNOW) AND THE ELEVATION MEANS THAT ANOTHER TANK OVERFLOWS
$
$$
$$$$
$$$$$$$$$$$
We Want to Have Well-Planned Projects To Keep Costs Low, and Projects Functioning Properly After They Are In Operation.

## Slide 12: Part of Planning: Understanding Initial Starting Place & Overall Needs Builds Into a Consideration of How The Assets Will Need to be Managed Into the Future (O&M, Repair, Replacement)

## Slide 13: Asset Management is One Type of Planning That Can be Very Helpful With Infrastructure Projects
Asset Management Involves…

## Slide 14: Identifying What Assets You Have
How Many, What Type, Location, Condition, Useful Life Remaining, & Replacement Cost

## Slide 15
Understanding What You Want Your Assets to Do
How Well Are Your Assets Doing That?
Are You Meeting Customer Expectations?

## Slide 16: Figuring Out Which Assets Are Critical to Sustained Operations Which Assets Are Likely to Fail and What Are the Consequences of the Failure?

## Slide 17
Thinking About the Assets Over Their Entire Life
When is the Best Time to Intervene? What Interventions Are Possible at Each Stage? What’s the Most Efficient Way to Intervene?

## Slide 18
Financial Resources
Where does the money come from?
Considering Long-Term Funding for Sustainability
How Much Money Do You Need? Where Will it Come From? What Do You Need Over the Life of the Facility (50 to 100 Years)?

## Slide 19
A Good, Comprehensive Map of Your Assets
An Asset Inventory (A List of All of Your Assets and Their Characteristics)
A Short and Long Term Capital Improvement Plan
An Understanding of the Current O&M Requirements
What Asset Management Activities Can
be Particularly Helpful in This Process?

## Slide 20: Another Part of Planning is Asking Questions
Is This the Right Project?
Is This the Right Time to Do the Project?
What are the Risks if I Don’t Take This Project On Right Now?
What are the Benefits if I Do the Project?
Is This Project Being Timed to Correspond to Another Activity (e.g., Road Paving, Expansion)

## Slide 21: If the Answer is: Not the Right Project or Not the Right Time For the Project, Stop Here & Re-Evaluate
Remember: This is the Time with the Greatest Influence at the Least Cost

## Slide 22: If the Answer is: The Right Project At The Right Time, Move To Design

## Slide 23: During Design You Will be Working With Engineers: Two Main Considerations for Today
Operations
Alternatives Evaluation

## Slide 24
Alternatives Evaluation

## Slide 25: Alternatives Evaluation
Questions to Ask:
Are All Viable Alternatives Considered?
Are They All Given Equal Consideration or is the Alternative Pre-Ordained?
Are Water System Personnel Able to Suggest Alternatives?
  If so, are All These Options Given Consideration by the Design Engineer?

## Slide 26: Alternatives Evaluation
Questions to Ask:
Are the Long-Term Costs of the Alternatives Taken into Consideration or Just the Initial Costs?
Is Energy Efficiency/Energy Use Considered in the Alternatives Process?
Is Water Efficiency Considered?

## Slide 27: Alternatives Evaluation
Questions to Ask:
Are New Technologies Considered or Just Standard Technologies?
If New Technologies are Considered, are You Given Examples of Utilities Using the Technology? Are You Given a Chance to Speak to These Utilities About Their Experiences?

## Slide 28: Alternatives Evaluation
Questions to Ask:
What Does the Write Up of the Alternatives Look Like? Are They Written Up as if All Were Considered Equally?
What Does the Costing Portion Look Like? Were All Alternatives Given the Same Level of Costing?

## Slide 29: Alternatives Evaluation
A Few Examples:
A Water System Was Given a Reverse Osmosis System When it Was Not Needed
A System Whose Alternative Evaluation Process Ignored Cheaper, Better Alternatives; Had to be Rejected By the SRF Agency During Review

## Slide 30: Alternatives Evaluation
Consider How This Process Has Worked in the Past:
How Involved Have You Been Able to be?
Do You Feel Like You Get the Best Alternative?
Do You Believe Other Alternatives Might Be Better?
Have You Had Any Cases Where A Different Alternative Would Have Been Better?

## Slide 31: Recall That Intervening During the Design Phase Still Allows You to Exert a Lot of Influence at a Relatively Low Cost. The More Involved You are the Better Chance to Have a Long-Term Impact
Figure 2. Relationship between influence and expenditures over project lifetime2

## Slide 32: Even Making a Change at 90% Design Might Be the Best Decision For the Long-Term of the Facility
Figure 2. Relationship between influence and expenditures over project lifetime2

## Slide 33
Operations & Design Is An Important Collaboration

## Slide 34
Operations & Design Should
Be A Collaborative Relationship
How Involved Are Operations Personnel In Design Discussions? Who is Involved in the Discussions?
What is the Primary Focus of the Discussions?
At What Point in the Process Do They Occur?

## Slide 35
If You Do Involve Operations, Do Your Engineers Usually Listen to You?
Do the Engineers Speak
in a Manner You Can
Understand?
If Not, Do You Ask for Them to Explain it in Other Terms?

## Slide 36
Remember, You Know the Specifics of the System Better Than Anyone Else
While the Engineer Knows How To Make Something Work, He/She May Not Be Well-Versed in The Operational Implications of the Design

## Slide 37
Design and Operations are Inextricably Intertwined: The Best Design Won’t Achieve its Intended Purpose Without Good Operations

## Slide 38
Likewise, the Best Operations Will Not Fix a Poor Design

## Slide 39
It is Extremely Important to Think Through Operations as an Integral Part of Design
Remember: By Operations, Least Influence at the Highest Cost

## Slide 40
Considerations of Operations in Design
What are the Major Activities Required in Routine Operation of Each Asset Included in the Design?
What Maintenance is Required?

## Slide 41
Considerations of Operations in Design
What Spare Parts are Required? Where are They Purchased? What is the Cost of the Parts?
What Level of Certification Will Be Required to Operate the New Facility? Is This Different Than the Prior Facility?

## Slide 42
Considerations of Operations in Design
What Level of Specialized Training is Required, if Any?
What Number of Operators Will Be Required to Operate the New Facility? Is That Different Than the Existing Facility?

## Slide 43
Original Design

## Slide 44: Retrofit After The Fact

## Slide 45: Another Example: Change Made During Design
Water Treatment Plant with Glass Control Room

## Slide 46: Important to Remember a Whole Project is Capital AND Operations

## Slide 47: After the Project is Constructed, You Will Have to Operate It For The Next 25, 50, 75, … Years

## Slide 48
Once You Are Ready to Do A Project it is A Good Idea to Set Project Milestones
Milestones are Major and Minor Tasks Along the Way to Completing the Project

## Slide 49
Project Initiation
Project Completion
First Milestones: The Major Boundaries

## Slide 50
Project Initiation
Project Completion
What are the Activities, Outputs, and Outcomes Associated with the Boundary Conditions

## Slide 51
VS

## Slide 52
What Is Created
The Numeric Results
Does Not Involve A Consideration of Quality; Considers Quantity

## Slide 53
Examples:
The Number of People Served By A Water System
The Number of Gallons of Water Produced
The Number of Miles of Pipe Put in the Ground

## Slide 54
The Level of Performance, Achievement, or Quality that Occurred Because of the Activity
An Assessment of the Success of the Process

## Slide 55
Examples:
The Increase in the % of People Served By Water Meeting EPA’s Primary Drinking Water Standards
Reduction of a Particular Contaminant in the Drinking Water (e.g., Reduced Arsenic Concentration)

## Slide 56
Both Are Needed to Assess the Effectiveness of the Project
Outputs Are Usually Easier to Measure and Faster to Achieve; Outcomes Take Longer to See But May Better Define Success

## Slide 57
Building Projects to Achieve Outcomes:
Describe the Outcomes You Are Trying to Achieve with the Project (Why Are You Doing the Project At All?)
Turn the Outcomes You Want to Achieve (Item 1) into Something That Can Be Measured (e.g., % Increase in Customers Served By Compliant Drinking Water or % Increase in Number of Customers Served By a Community Water System)
If You Can’t Answer This Question Effectively, You Shouldn’t Be Doing The Project

## Slide 58
Building Projects to Achieve Outcomes:
Confirm That the Outcomes Are Linked to the Outputs and Activities
  (Can You Expect to Achieve the Outcomes Based on What You Are Doing?)
Implement the Measurement of Outcomes and Track Achievement For Funding Agencies, Regulatory Agencies, Elected Leaders and Customers

## Slide 59
Project Initiation
Project Completion
Determine the Outputs and Outcomes Associated With the Boundary Conditions
Expected Outputs:___
Expected Outcomes: ___

## Slide 60
Project Initiation
Project Completion
What Activities Are Needed to Achieve the Expected Outputs, and Outcomes?
Activities Needed to Achieve Expected Outputs and Outcomes
Expected Outputs: ___
Expected Outcomes: ___

## Slide 61
Project Initiation
Project Completion
Place Each Major Activity Needed to Achieve Outputs and Outcomes on Milestone Graph
Expected Outputs:___
Expected Outcomes: ___
Major Activity 2
Major Activity 3
Major Activity 4
Major Activity 1

## Slide 62
Project Initiation
Project Completion
Are There Minor Activities That Take Place Between the Major Activities? If So, Add Them to the Milestone Graph
Expected Outputs:___
Expected Outcomes: ___
Major Activity 2
Major Activity 3
Major Activity 4
Major Activity 1
Minor Activity 1
Minor Activity 2
Minor Activity 3
Minor Activity 4
Minor Activity 5
Minor Activity 6

## Slide 63
Project Initiation
Project Completion
Check Over the Listing of Major and Minor Activities – Will These Activities Be Sufficient to Achieve the Desired Outputs and Outcomes? If Not, Add More
Expected Outputs:___
Expected Outcomes: ___
Major Activity 2
Major Activity 3
Major Activity 4
Major Activity 1
Minor Activity 1
Minor Activity 2
Minor Activity 3
Minor Activity 4
Minor Activity 5
Minor Activity 6

## Slide 64
Project Initiation
Project Completion
Once All the Major and Minor Activities Necessary Are Included on the Graph, Add Schedule
Expected Outputs:___
Expected Outcomes: ___
Major Activity 2
Major Activity 3
Major Activity 4
Major Activity 1
Minor Activity 1
Minor Activity 2
Minor Activity 3
Minor Activity 4
Minor Activity 5
Minor Activity 6

## Slide 65
Project Initiation
Project Completion
Start with the Project Initiation Date and Anticipated Completion Date
Expected Outputs:___
Expected Outcomes: ___
Major Activity 2
Major Activity 3
Major Activity 4
Major Activity 1
Minor Activity 1
Minor Activity 2
Minor Activity 3
Minor Activity 4
Minor Activity 5
Minor Activity 6
May 2019
Sept 2022

## Slide 66
Project Initiation
Project Completion
Work with Engineer & Funder(s) to Fill in the Remaining Dates
Expected Outputs:___
Expected Outcomes: ___
Major Activity 2
Major Activity 3
Major Activity 4
Major Activity 1
Minor Activity 1
Minor Activity 2
Minor Activity 3
Minor Activity 4
Minor Activity 5
Minor Activity 6
May 2019
Sept 2022
Oct 2019
Mar 2020
Aug 2020
Nov 2020
Jan 2021
May 2021
Sep 2021
Nov 2021
Feb 2022
July 2022

## Slide 67
Project Initiation
Project Completion
Work w/Engineer & Funder(s) to Fill in the Total Project Cost
Expected Outputs:___
Expected Outcomes: ___
Major Activity 2
Major Activity 3
Major Activity 4
Major Activity 1
Minor Activity 1
Minor Activity 2
Minor Activity 3
Minor Activity 4
Minor Activity 5
Minor Activity 6
May 2019
Sept 2022
Oct 2019
Mar 2020
Aug 2020
Nov 2020
Jan 2021
May 2021
Sep 2021
Nov 2021
Feb 2022
July 2022
$2.5 M

## Slide 68
Project Initiation
Project Completion
Work w/Engineer & Funder(s) to Fill in the Rest of the Costs
Expected Outputs:___
Expected Outcomes: ___
Major Activity 2
Major Activity 3
Major Activity 4
Major Activity 1
Minor Activity 1
Minor Activity 2
Minor Activity 3
Minor Activity 4
Minor Activity 5
Minor Activity 6
May 2019
Sept 2022
Oct 2019
Mar 2020
Aug 2020
Nov 2020
Jan 2021
May 2021
Sep 2021
Nov 2021
Feb 2022
July 2022
$2.5 M
$70 K
$250 K
$90 K
$550 K
$125 K
$150 K
$750 K
$350 K
$85 K
$80 K

## Slide 69: Create a Table with Major and Minor Activities (Tasks), including Completion Date and Costs
Task | Expected Completion Date | Anticipated Cost | Anticipated Cumulative Cost
Project Initiation | May 2019 |  | 
Minor Activity 1 | Oct 2019 | $80,000 | $80,000
Minor Activity 2 | Mar 2020 | $85,000 | $165,000
Major Activity 1 | Aug 2020 | $350,000 | $515,000
Major Activity 2 | Nov 2020 | $750,000 | $1,265,000
Minor Activity 3 | Jan 2021 | $150,000 | $1,415,000
Minor Activity 4 | May 2021 | $125,000 | $1,540,000
Major Activity 3 | Sep 2021 | $550,000 | $2,090,000
Minor Activity 5 | Nov 2021 | $90,000 | $2,180,000
Major Activity 4 | Feb 2022 | $250,000 | $2,430,000
Minor Activity 6 | July 2022 | $70,000 | $2,500,000
Project Completion | Sept 2022 | $2,500,000 | $2,500,000

## Slide 70: Create a Table with Major and Minor Activities (Tasks), including Completion Date and Costs
Task | Expected Completion Date | Anticipated Cost | Anticipated Cumulative Cost
Project Initiation | May 2019 |  | 
Minor Activity 1 | Oct 2019 | $80,000 | $80,000
Minor Activity 2 | Mar 2020 | $85,000 | $165,000
Major Activity 1 | Aug 2020 | $350,000 | $515,000
Major Activity 2 | Nov 2020 | $750,000 | $1,265,000
Minor Activity 3 | Jan 2021 | $150,000 | $1,415,000
Minor Activity 4 | May 2021 | $125,000 | $1,540,000
Major Activity 3 | Sep 2021 | $550,000 | $2,090,000
Minor Activity 5 | Nov 2021 | $90,000 | $2,180,000
Major Activity 4 | Feb 2022 | $250,000 | $2,430,000
Minor Activity 6 | July 2022 | $70,000 | $2,500,000
Project Completion | Sept 2022 | $2,500,000 | $2,500,000
Look At Expenditures – How Are Costs Spread Out Over Time? Are There Long Periods With No Expenditures? Are Costs Higher Up Front, or in the Middle, or at the End?

## Slide 71: Create a Table with Major and Minor Activities (Tasks), including Completion Date and Costs
Task | Expected Completion Date | Anticipated Cost | Anticipated Cumulative Cost
Project Initiation | May 2019 |  | 
Minor Activity 1 | Oct 2019 | $80,000 | $80,000
Minor Activity 2 | Mar 2020 | $85,000 | $165,000
Major Activity 1 | Aug 2020 | $350,000 | $515,000
Major Activity 2 | Nov 2020 | $750,000 | $1,265,000
Minor Activity 3 | Jan 2021 | $150,000 | $1,415,000
Minor Activity 4 | May 2021 | $125,000 | $1,540,000
Major Activity 3 | Sep 2021 | $550,000 | $2,090,000
Minor Activity 5 | Nov 2021 | $90,000 | $2,180,000
Major Activity 4 | Feb 2022 | $250,000 | $2,430,000
Minor Activity 6 | July 2022 | $70,000 | $2,500,000
Project Completion | Sept 2022 | $2,500,000 | $2,500,000
Generally, Costs Should Ramp Up At the Beginning to a Higher Level in the Middle and Then Ramp Down to a Lower Level At the End As the Project Slows Down.

## Slide 72: Create a Table with Major and Minor Activities (Tasks), including Completion Date and Costs
Task | Expected Completion Date | Anticipated Cost | Anticipated Cumulative Cost
Project Initiation | May 2019 |  | 
Minor Activity 1 | Oct 2019 | $80,000 | $80,000
Minor Activity 2 | Mar 2020 | $85,000 | $165,000
Major Activity 1 | Aug 2020 | $350,000 | $515,000
Major Activity 2 | Nov 2020 | $750,000 | $1,265,000
Minor Activity 3 | Jan 2021 | $150,000 | $1,415,000
Minor Activity 4 | May 2021 | $125,000 | $1,540,000
Major Activity 3 | Sep 2021 | $550,000 | $2,090,000
Minor Activity 5 | Nov 2021 | $90,000 | $2,180,000
Major Activity 4 | Feb 2022 | $250,000 | $2,430,000
Minor Activity 6 | July 2022 | $70,000 | $2,500,000
Project Completion | Sept 2022 | $2,500,000 | $2,500,000
If There Are Long Periods With No Expenditures Anticipated, Consider Adding Minor Tasks To Spread Out Expenditures

## Slide 73
During the Project, Check Actual Activities, Schedules, and Expenditures Against the Planned Ones

## Slide 74
Project Initiation
Project Completion
Expected Outputs:___
Expected Outcomes: ___
Major Activity 2
Major Activity 3
Major Activity 4
Major Activity 1
Minor Activity 1
Minor Activity 2
Minor Activity 3
Minor Activity 4
Minor Activity 5
Minor Activity 6
May 2019
Sept 2022
Oct 2019
Mar 2020
Aug 2020
Nov 2020
Jan 2021
May 2021
Sep 2021
Nov 2021
Feb 2022
July 2022
$2.5 M
$70 K
$250 K
$90 K
$550 K
$125 K
$150 K
$750 K
$350 K
$85 K
$80 K
July 2019
Nov 2022
Dec 2019
Apr 2020
Oct 2020
Jan 2021
Mar 2021
Jun 2021
Nov 2021
Jan 2022
Apr 2022
Sep 2022
Look For Places Where Actuals Don’t Match Anticipated

## Slide 75
Project Initiation
Project Completion
Expected Outputs:___
Expected Outcomes: ___
Major Activity 2
Major Activity 3
Major Activity 4
Major Activity 1
Minor Activity 1
Minor Activity 2
Minor Activity 3
Minor Activity 4
Minor Activity 5
Minor Activity 6
May 2019
Sept 2022
Oct 2019
Mar 2020
Aug 2020
Nov 2020
Jan 2021
May 2021
Sep 2021
Nov 2021
Feb 2022
July 2022
$2.5 M
$70 K
$250 K
$90 K
$550 K
$125 K
$150 K
$750 K
$350 K
$85 K
$80 K
July 2019
Nov 2022
Dec 2019
Apr 2020
Oct 2020
Jan 2021
Mar 2021
Jun 2021
Nov 2021
Jan 2022
Apr 2022
Sep 2022
Look for Places Where Actuals Don’t Match Anticipated
What Caused the Project to Go Off Schedule? Is There Any Way to Get the Project Back On Schedule?
Will the Slip in the Project Schedule Cause a Change in Costs? If So, How?
Will the Slippage in the Schedule Cause a Problem With Regulatory Compliance?

## Slide 76: Track Actual Costs Against Anticipated Costs
Task | Anticipated Cost | Actual Cost | Difference (Over or Under Budget)
Project Initiation |  |  | 
Minor Activity 1 | $80,000 | $90,000 | $10,000
Minor Activity 2 | $85,000 | $120,000 | $35,000
Major Activity 1 | $350,000 | $425,000 | $75,000
Major Activity 2 | $750,000 | $750,000 | $0
Minor Activity 3 | $150,000 | $175,000 | $25,000
Minor Activity 4 | $125,000 | $140,000 | $15,000
Major Activity 3 | $550,000 | $550,000 | $0
Minor Activity 5 | $90,000 | $100,000 | $10,000
Major Activity 4 | $250,000 | $250,000 | $0
Minor Activity 6 | $70,000 | $150,000 | $80,000
Project Completion | $2,500,000 | $2,750,000 | $250,000

## Slide 77: Track Actual Costs Against Anticipated Costs
Task | Anticipated Cost | Actual Cost | Difference (Over or Under Budget)
Project Initiation |  |  | 
Minor Activity 1 | $80,000 | $90,000 | $10,000
Minor Activity 2 | $85,000 | $120,000 | $35,000
Major Activity 1 | $350,000 | $425,000 | $75,000
Major Activity 2 | $750,000 | $750,000 | $0
Minor Activity 3 | $150,000 | $175,000 | $25,000
Minor Activity 4 | $125,000 | $140,000 | $15,000
Major Activity 3 | $550,000 | $550,000 | $0
Minor Activity 5 | $90,000 | $100,000 | $10,000
Major Activity 4 | $250,000 | $250,000 | $0
Minor Activity 6 | $70,000 | $150,000 | $80,000
Project Completion | $2,500,000 | $2,750,000 | $250,000
If the Expenses Are Over Anticipated Costs, What Are the Reasons for the Over-expenditure? Is There Any Way to Get the Project Back on Track?
Is There an Impact On the Ability to Get the Project Completed At All? How Are Over-Expenditures Addressed?

## Slide 78: Track Actual Costs Against Anticipated Costs
Task | Anticipated Cost | Actual Cost | Difference (Over or Under Budget)
Project Initiation |  |  | 
Minor Activity 1 | $80,000 | $90,000 | $10,000
Minor Activity 2 | $85,000 | $120,000 | $35,000
Major Activity 1 | $350,000 | $425,000 | $75,000
Major Activity 2 | $750,000 | $750,000 | $0
Minor Activity 3 | $150,000 | $175,000 | $25,000
Minor Activity 4 | $125,000 | $140,000 | $15,000
Major Activity 3 | $550,000 | $550,000 | $0
Minor Activity 5 | $90,000 | $100,000 | $10,000
Major Activity 4 | $250,000 | $250,000 | $0
Minor Activity 6 | $70,000 | $150,000 | $80,000
Project Completion | $2,500,000 | $2,750,000 | $250,000
If Expenses Are Less Than Anticipated, What Can Be Done With the Extra Funds? Can Additional Work Be Done or Will the Money Be Returned?

## Slide 79
During the Project, Consider Whether the Anticipated Outputs and Outcomes Are Being Achieved

## Slide 80
Is the Project Able to Meet the Desired Outputs and Outcomes? If No, Which Ones Won’t Be Achieved and What Will Be Done About It?

## Slide 81
If yes, Measure the Ability to Meet the Outcomes and Measure the Outputs

## Slide 82
Consider If Problems With the Budget or Schedule Have Impacted the Ability to Meet Project Outputs and Outcomes

## Slide 83: Financial Fundamentals
PRESENTED BY HEATHER HIMMELBERGER, P.E. Director, SW EFC
Finally, We’ll Talk a Little About Finance:
Accounting, Bookkeeping, Reporting

## Slide 84
Accounting Encompasses the Broader Responsibilities Over Developing and Maintaining the Financial Systems Under Which Bookkeeping and Reporting Functions Are Preformed
Input
Output

## Slide 85
Accounting is Concerned With Timely and Accurate Recording of Transactions, Providing Useful Information, for Management and Properly Reporting Such Information for Various People’s Needs, Including Funders.
Input
Output

## Slide 86
Goals of Bookkeeping:
  Keep Track of Income and Expenses, Thereby Improving the Organization’s Ability to Ensure More Money Comes in Than Goes Out (Revenue > Expenses)
  Collect the Necessary Financial Information to File Required Reports
Input
Output

## Slide 87
Bookkeeping Refers to the Actual Transactional Entering and Recording of Data. Examples Include: Writing Checks, Processing Payroll, Making Deposits, Recording Disbursements and Recording Receipts
Input
Output

## Slide 88
Reporting: The Output of the Data Generated Through Various Bookkeeping Entries Is Used for Both Internal and External Purposes. Internal Reports Are Used Within the Organization By Management and Other Personnel. External Reporting Can Be Used By Individuals Outside the Organization.
Input
Output

## Slide 89: The Financial Process
1. Identify and Record Transactions
2. Reconcile and Analyze Accounts
3. Summarize into Monthly or Quarterly Report
4. Year End Audit
5. Repeat

## Slide 90: Cost Sharing and Matching
The Portion of the Project That A Recipient Contributes Towards the Project
May Be Required To Be Cash or Sometimes In-kind Is Allowed
May Be Voluntary or Mandatory

## Slide 91: Cost Sharing and Matching Paperwork
Must Be Documented
Must Be Documented in the Same Manner As Other Costs
Paperwork Supporting In-kind Must Be Kept

## Slide 92: Progress Reports
Just About Every (If Not Every) EPA Project of Any Type Has Requirements for Progress Reporting, Many Other Agencies Do As Well
Monthly, Quarterly, Semi-annually or Annual
Check To See What the Requirement Is for Your Grant And What The Due Date Is (Usually 30 Days following The End of The Reporting Period)
Establish A Means of Alerting You That A Report Is Due

## Slide 93: Progress Reports
Try To Develop An Easy Way To Complete the Report
Don’t Wait Too Long To Do the Documentation
For Example, Have A Set Place To Write Down Any Significant Item That You Completed in the Week or Month
Have A Set Format (Standardized Is Easier To Follow And Recreate).

## Slide 94: Spending Grant Funds
Comply With Internal & External Regulations, Policies, and Procedures
Consider Audit Readiness for Every Transaction
Review Expenditures vs Budget on Every Transaction
No Supplanting or Cost-shifting

## Slide 95: Spending Grant Funds
How Do You Become Aware of the Specific Requirements of the Grant?
Do You Have A Checklist or Any Other Process to Keep Abreast of the Requirements and Your Particular Role in Complying With Them?

## Slide 96: Documentation
Document Everything
Save All Documents
Keep All Documents Pertaining to a Single Project Together
Keep Everything With a Signature
Store in a Safe Place, Both Electronic and Paper Records
Have Back Ups (Both Electronic and Paper) in Multiple Places

## Slide 97: There Are Regulations That Govern How Grants Are Managed, How Payments Are Made, When Payments Are Made, and Many Other Things. Know the Regulations BEFORE the Projects Starts.

## Slide 98: Every Grant or Loan Has Specific Reporting Requirements That Should Be Understood and Followed

## Slide 99: In Summary…

## Slide 101
CONTACT INFORMATION
Department of Civil Engineering MSC01 1070
1 University of New Mexico, Albuquerque, NM 87131
505-277-0644
swefc@unm.edu
http://southwestefc.unm.edu
Heather Himmelberger: heatherh@unm.edu
Dawn Nall: dnall@unm.edu
James Markham: jmarkham@unm.edu